## Sheet1
| date | work documents | findings | reporter
1 | 25/4/2024 | class diagram | missing attributes car page class and car reservation class need to be merged functions need modifications and renaming in most classes | bassant samir
|  | Wireframe | modifications in car listing page and registration page | bassant samir
|  | high level decomposition | removing database as a module and simplifying the overall diagram | amr
|  | flow charts | adding database steps | amr
2 | 2024-05-05 | database | advertise and reserve tables needs modifying | bassant samir
|  |  | phone number for user needs modifying | alzahraa mahmoud
|  |  | removing auto increment from phone number | amira bahaa
|  | car search module | modifying UI | bassant samir
3 | 2024-07-05 | car advertisement | modifying UI | bassant samir