## Sheet1
Sprint | Deliverables | Tasks | Deadline | Submittion Date | Assignee | Availability | Estimated Effort | Actual Effort | Status
Sprint 1 | PMP | Objective | 16-3-2024 | 16-3-2024 | Alzahraa Mahmoud | 4 | 15 minutes | 5 minutes | Approved
|  | Scope | 16-3-2024 | 16-3-2024 | Alzahraa Mahmoud |  | 0.5 | 0.5 | Approved
|  | Configuration Management Plan | 25-3-2024 | 29-3-2024 | Alzahraa Mahmoud |  | 1 | 45 minutes | Approved
|  | Change Requests Management Plan | 25-3-2024 | 22-3-2024 | Bassant Samir | 4 | 0.5 | 0.5 | Approved
|  | Risk Management Plan | 25-3-2024 | 24-3-2024 | Bassant Samir |  | 1 | 1 | Approved
|  | Stakeholders Involvement Plan | 25-3-2024 | 23-3-2024 | Bassant Samir |  | 0.5 | 15 minutes | Approved
|  | Review Process | 25-3-2024 | 29-3-2024 | Bassant Samir |  | 0.5 | 0.5 | Approved
|  | Roles | 16-3-2024 | 16-3-2024 | Bassant Samir |  | 10 minutes | 5 minutes | Approved
|  | Problem Resolution Plan | 25-3-2024 | 23-3-2024 | Bassant Samir |  | 1 | 1 | Approved
| SIQ |  | 16-3-2024 | 16-3-2024 | Ashraqat Hassan | 4 | 1 | 1 | Approved
| Task Board |  | 16-3-2024 | 16-3-2024 | Muhammed Magdy | 4 | 1 | 0.5 | Approved
| SRS draft | Overall Description | 25-3-2024 | 16-3-2024 | Angelous Adel | 4 | 3 | 2 | Approved
|  | Specific Requirements | 25-3-2024 | 16-3-2024 | Amira Bahaa | 4 | 3 | 2 | Approved
Sprint 2 | RTM | Customer Requirements | 31-3-2024 | 31-3-2024 | Ashraqat Hassan | 2 | 1 | 40 minutes | Approved
|  | RTM template | 2024-03-04 | 2024-03-04 | Muhammed Magdy | 3 | 1.5 | 1 | Approved
|  | Feature Validations | 2024-07-04 | 2024-08-04 | Muhammed Magdy |  | 1 |  | Approved
| Full SRS | Functional Requirements IDs | 2024-03-04 | 2024-03-04 | Angelous Adel | 2 | 0.5 | 0.5 | Approved
|  | Feature Validations | 2024-05-04 | 2024-05-04 | Angelous Adel |  | 1.5 | 1 | Approved
|  | Feature Descriptions | 2024-07-04 | 2024-07-04 | Amira Bahaa | 3 | 1.5 | 1 | Approved
|  | Feature Descriptions | 2024-07-04 | 2024-07-04 | Alzahraa Mahmoud | 3 | 1.5 | 1 | Approved
|  | modifications | 14-4-2024 | 14-4-2024 | Bassant Samir | 3 | 1 | 1 | Approved
| PMP modifications | Revision History | 2024-06-04 | 2024-05-04 | Bassant Samir |  | 0.5 | 15 minutes | Approved
|  | Content Modifications | 2024-06-04 | 2024-05-04 | Bassant Samir |  | 0.5 |  | Approved
Sprint 3 | Design | ERD | 21-4-2024 | 20-4-2024 | Angelous Adel | 8 | 3 | 3 | Approved
|  | Wireframe | 24-4-2024 | 25-4-2024 | Angelous Adel |  | 3 | 3 | Approved
|  | ERD | 21-4-2024 | 20-4-2024 | Amira Bahaa | 8 | 3 | 3 | Approved
|  | High Level Description | 24-4-2024 | 25-4-2024 | Amira Bahaa |  | 2 | 1.5 | Approved
|  | RTM | 26-4-2024 |  | Amira Bahaa |  | 0.5 |  | Deferred
|  | Wireframe | 24-4-2024 | 25-4-2024 | Ashraqat Hassan | 8 | 3 | 3 | Approved
|  | Use Cases | 21-4-2024 | 20-4-2024 | Ashraqat Hassan |  | 2 | 2 | Approved
|  | Use Cases | 21-4-2024 | 20-4-2024 | Muhammed Magdy | 8 | 2 | 2 | Approved
|  | Class Diagrams | 24-4-2024 | 25-4-2024 | Muhammed Magdy |  | 4 | 3 | Reviewed
|  | Class Diagrams modifications | 26-4-2024 | 26-4-2024 | Alzahraa Mahmoud | 8 | 1 | 1 | Reviewed
|  | Flow Charts | 26-4-2024 | 26-4-2024 | Alzahraa Mahmoud |  | 3 | 5 | Reviewed
|  | CMP modifications | 24-4-2024 | 26-4-2024 | Alzahraa Mahmoud |  | 0.5 | 0.5 | Reviewed
|  | Sequence Diagrams | 26-4-2024 | 26-4-2024 | Alzahraa Mahmoud |  | 2 | 3 | Reviewed
|  | Flow Charts | 26-4-2024 | 23-4-2024 | Bassant Samir | 8 | 3 | 5 | Reviewed
|  | PMP modifications | 24-4-2024 | 26-4-2024 | Bassant Samir |  | 1 | 0.5 | Reviewed
|  | Time Plan | 22-4-2024 | 22-4-2024 | Bassant Samir |  | 1 | 0.8 | Reviewed
|  | Sequence Diagrams | 26-4-2024 | 26-4-2024 | Bassant Samir |  | 2 | 3 | Reviewed
|  | Class Diagrams modifications | 26-4-2024 | 26-4-2024 | Bassant Samir |  | 1 | 1 | Reviewed
Sprint 4 | LLD modifications | Modifications | 2024-10-05 |  | Bassant Samir | 1 | 1 | 2 | Completed
|  | Review | 2024-10-05 |  | Alzahraa Mahmoud | 1 | 0.5
| Login Module | Development | 2024-07-05 | 2024-05-05 | Bassant Samir | 4 | 4 | 5 | Reviewed
|  | Modifications | 2024-08-05 | 2024-07-05 | Bassant Samir | 1 | 1 | 1 | Reviewed
|  | Review | 2024-07-05 | 2024-05-05 | Alzahraa Mahmoud | 1 | 0.5 | 0.5
| Registration Module | Development | 2024-07-05 | 2024-05-05 | Alzahraa Mahmoud | 4 | 4 |  | In Progress
|  | Modifications | 2024-08-05 |  | Alzahraa Mahmoud | 1 | 1 |  | Not Started
|  | Review | 2024-07-05 |  | Bassant Samir | 1 | 0.5
| Car Listing Module | UI | 2024-06-05 | 2024-07-05 | Angelous Adel | 3 | 2 | 3 | Reviewed
|  | UI modifications | 2024-06-05 | 2024-07-05 | Angelous Adel | 1 | 1 | 1 | In Progress
|  | Redirection to car advertisement | 2024-07-05 | 2024-07-05 | Ashraqat Hassan | 1 | 1 | 1 | Reviewed
|  | Redirection to car search | 2024-07-05 | 2024-07-05 | Muhammed Magdy | 1 | 1 | 1 | Reviewed
|  | Retrieving search results from database | 2024-07-05 | 2024-10-05 | Muhammed Magdy | 2 | 2 | 8 | Reviewed
|  | Redirection to admin features | 2024-07-05 |  | Alzahraa Mahmoud | 2 | 1 |  | Deferred
|  | Redirection to car page | 2024-07-05 |  | Angelous Adel | 2 | 1 |  | Deferred
|  | Retrieving all cars from database | 2024-07-05 | 2024-07-05 | Amira Bahaa | 2 | 2 | 3 | Reviewed
| Car Search Module | Development | 2024-07-05 | 2024-07-05 | Muhammed Magdy | 6 | 5 | 10 | Reviewed
|  | Modifications | 2024-08-05 | 2024-10-05 | Muhammed Magdy | 1 | 1 | 4 | Reviewed
|  | Review | 2024-07-05 | 2024-10-05 | Amira Bahaa | 1 | 0.5 | 1
| Car Advertisement Module | Development | 2024-07-05 | 2024-07-05 | Ashraqat Hassan | 6 | 4 |  | In Progress
|  | Modifications | 2024-08-05 | 2024-10-05 | Ashraqat Hassan | 1 | 1 |  | Not Started
|  | Review | 2024-07-05 |  | Angelous Adel | 1 | 0.5
| Car Page Module | Development | 2024-07-05 |  | Angelous Adel | 4 | 4 |  | Deferred
|  | Modifications | 2024-08-05 |  | Angelous Adel | 1 | 1 |  | Deferred
|  | Review | 2024-07-05 |  | Ashraqat Hassan | 1 | 0.5
| Admin Features Module | UI | 2024-06-05 |  | Ashraqat Hassan | 3 | 2 |  | Deferred
|  | Deleting user | 2024-07-05 |  | Bassant Samir | 2 | 1.5 |  | Deferred
|  | Deleting car | 2024-07-05 |  | Alzahraa Mahmoud | 2 | 1.5 |  | Deferred
| Database | Development | 2024-06-05 | 2024-05-05 | Amira Bahaa | 8 | 6 | 7 | Reviewed
|  | Modifications | 2024-07-05 | 2024-06-05 | Bassant Samir | 2 | 1 | 3 | Reviewed
|  | Review | 2024-06-05 | 2024-05-05 | Bassant Samir | 1 | 1 | 1