## Sheet1
Sprint | Deliverables | Tasks | Deadline | Assignee | Availability | Estimated Effort | Actual Effort | Status
Sprint 1 | PMP | Objective | 16-3-2024 | Alzahraa Mahmoud | 4 hour | 15 minutes | 5 minutes | Reviewed
|  | Scope | 16-3-2024 | Alzahraa Mahmoud | 4 hour | 30 minutes | 30 minutes | Reviewed
|  | Configuration Management Plan | 29-3-2024 | Alzahraa Mahmoud | 4 hour | 1 hour | 45 minutes | Reviewed
|  | Change Requests Management Plan | 25-3-2024 | Bassant Samir | 4 hour | 30 minutes | 20 minutes | Reviewed
|  | Risk Management Plan | 25-3-2024 | Bassant Samir | 4 hour | 1 hour | 1 hour | Reviewed
|  | Stakeholders Involvement Plan | 25-3-2024 | Bassant Samir | 4 hour | 30 minutes | 15 minutes | Reviewed
|  | Review Process | 29-3-2024 | Bassant Samir | 4 hour | 30 minutes | 30 minutes | Completed
|  | Roles | 16-3-2024 | Bassant Samir | 4 hour | 10 minutes | 5 minutes | Reviewed
|  | Problem Resolution Plan | 25-3-2024 | Bassant Samir | 4 hour | 1 hour | 1 hour | Reviewed
| SIQ |  | 16-3-2024 | Ashraqat Hassan | 4 hour | 1 hour |  | Reviewed
| Task Board |  | 16-3-2024 | Muhammed Magdy | 4 hour | 1 hour |  | Reviewed
| SRS | Overall Description | 25-3-2024 | Angelous Adel | 4 hour | 3 hours | 2 hours | Reviewed
|  | Specific Requirements | 25-3-2024 | Amira Bahaa | 4 hour | 3 hours | 2 hours | Reviewed
| Design | ERD
Relation Diagram
Review
Modules Planning
| Login Module | Development
Testing
Review
| Registeration Module | Development
Testing
Review
| Search Module | Development
Testing
Review
| Search Result Module | Development
Testing
Review
| Car Details Module | Development
Testing
Review